## CAD Plan
Needs to be morphed/interpart expressions |  |  |  |  | Total Weight
No interpart expressions nescesary |  |  |  |  | 6 lb 6 oz
Master Assembly(1A)
Sub-Assembly Name | Part Name | qty | Progress | Owner
Structure | Chassis | 1 | Done | Zach
| Chassis Handle | 2 | Done (GrabCad) | Jackson
| Shell - 6 oz | 1 | Done | Jackson
| Wheels - 4.3 oz / each | 4 | Done (GrabCad) | Jackson
Front Wheel Drive(1B) | Front Toe control(1C) | 2 | Done | Dawson
| Front Camber Control(2C) | 2 | Done | Jackson
| Front Lower Control Arm | 2 | Done | Alex
| Front Axles | 2 | Done | Dawson
| Front Sub Frame | 1 | Done | Jackson
| Front Upper Control Arm |  | Done | Jackson
| Front Bumper 1.9 oz | 1 | Done | Jackson
| Front Knuckles | 2 | Done | Alex
| Front Suspension (Shock) | 2 | Done (GrabCad) | Jackson
Rear Wheel Drive(2B) | Rear Camber Control | 2 | Done | Jackson
| Rear Lower Control Arm | 2 | Done (GrabCad) | Jackson
| Rear Axles | 2 | Done | Jackson
| Rear Sub Frame | 1 | Done | Jackson
| Rear Upper Control Arm | 1 | Done | Jackson
| Rear Bumper | 1 | Done | Jackson
| Rear Knuckles | 2 | Done | Jackson
| Rear Suspension (Shock) | 2 | Done (GrabCad) | Jackson
Steering Assembly(3B) | Steering Motor(download) | 1 | Done | Dawson
| Steering Linkage |  |  | Alex
Chasis Components (4B) | Battery | 1 | Done | Will
| Drive Motor | 1 | Done (GrabCad) | Dawson
| Transmission | 1 | Done | Will
| Motor Driver | 1 | Done | Will
| Computer Box | 1 | Done | Will
Naming Convention: SubAssy#_Part#_PartName, for example front camber control: 1B_2C_FrontCamber

## Online Cad
Item | Link
Shock | https://grabcad.com/library/e-maxx-t-maxx-rc-shock
Side Handle | https://grabcad.com/library/traxxas-5283-nerf-bars-1
Suspension Bar | https://grabcad.com/library/traxxas-slash-4x4-left-hand-a-arm-1
Wheels | https://grabcad.com/library/rc-wheel-1
Servo Motor

## Tracked Hours
Each member add total hours worked on project each week
Week | Jackson | Dawson | Alex | Will | Zach
2025-03-24 | 1.5 | 2 | 0 | 2 | 1.5
2025-03-31 | 27 | 8 | 4 | 6 | 7
2025-04-07 | 8 | 7 | 4 | 3 | 7
2025-04-14 | 23 | 8 | 6 | 4 | 12
2025-04-21 | 17 | 20 | 19 | 29
2025-04-28
Total Hours: | 76.5 | 45 | 33 | 44 | 27.5